## Summary
SPEC BID-REVIEW - read this first
Documents: sdps_special-provisions-full-07.08.21 | 406 pages |  | Trade watchlists: concrete, mep, finishes, universal
BID-KILLERS | Key value | Where | Clause
Bid due date / opening | Wednesday, September 8, 2021; 2:01 p.m | Section I. Proposal And Contra p6 | Bids will be opened in the Public Works Department, 950 W. Mall Square, Room 110, Alameda, California, at 2:01 p.m. on Wednesday, September 8, 2021. F. BIDDER'S GUARANTY. All bids shall be accompanied by one of the follo
Mandatory pre-bid / job-walk | Wednesday, August 18, 2021 at 11:00 am | Section I. Proposal And Contra p6 | A mandatory pre-bid meeting will be held at City Hall West, 950 W. Mall Square, Conference Room 156, Alameda, California, 94501 on Wednesday, August 18, 2021 at 11:00 am. City reserves the right to hold additional prebid
RFI / questions deadline | submit an RFI within five (5) business days | Section II. Legal Relations An p21 | X. SUBMITTALS AND REQUEST FOR INFORMATION (RFI'S). The Contractor shall submit an RFI within five (5) business days of an event or question of fact arising under the Contract. The Engineer in cha
Bid bond / bid security | 10% | Section I. Proposal And Contra p6 | The security shall be in an amount equal to at least ten percent (10%) of the amount bid. A bid shall not be considered unless one of the forms of bidder's security is enclosed with it.
Performance bond | $25,000 | Exhibit C p88 | Faithful Performance Bond and Labor and Material Bond are only required for work over $25,000. Therefore, those estimates that are under $25,000 will not need to budget for the bond premiums and those estimates over $25,
Payment bond | $25,000 | Exhibit C p88 | Faithful Performance Bond and Labor and Material Bond are only required for work over $25,000. Therefore, those estimates that are under $25,000 will not need to budget for the bond premiums and those estimates over $25,
Post-award bonds/insurance deadline |  | Section I. Proposal And Contra p8 | No proposal shall be considered binding upon the City until the execution of the contract. Failure to execute a contract and file acceptable bonds and insurance as provided herein within the time frame outlined above sha
Bid validity period | 90 days | Section I. Proposal And Contra p7 | In the event of a delay the City reserves the right to hold the Bidder to its bid for 90 days from the date the contract is awarded. Bid protests, contracts, bonds, insurance, and other documents identified in these spec
Liquidated damages | $2,500.00 per day | Section VI. Prosecution And Pr p34 | E. TIME OF COMPLETION AND LIQUIDATED DAMAGES. It is agreed by the parties to the contract that in case all the work called for under the contract is not completed before or upon the expiration of the contract's term as s
Per-day penalties / fines | $250.00 per occurrence per day | Section II. Legal Relations An p19 | The fine for noncompliance of the above program is two hundred and fifty dollars ($250.00) per occurrence per day. The State under the Federal Clean Water Act can also impose a fine on the Contractor.
Contract time / completion | two hundred fifty (250) consecutive working days | Section III. Scope Of Work p25 | The Contractor shall have two hundred fifty (250) consecutive working days from the date the work is to commence pursuant to the Notice to Proceed to complete the work. Contractor is advised to remove all equipment from
Insurance requirement |  | Exhibit C p86 | …terms of this Agreement, Contractor shall furnish the City's Risk Manager with certificates showing the type, amount, class of operations covered, effective dates and dates of expiration of insurance coverage in complia
Prevailing wage / Davis-Bacon | $50.00 for each calendar day | Section II. Legal Relations An p10 | …Industrial Relations determines that there has been a change in any prevailing rate of per diem wages in the locality in which this public work is to be performed, such change shall not alter the wage rates in the Notic
Required contractor license | "A" license or a "C" license | Section II. Legal Relations An p13 | All Contractors must have an "A" license or a "C" license that allows them to complete the work specified herein, in a professional manner consistent with these specifications. J. PERMITS AND LICENSES. The Contractor sha
Retainage |  | Section VII. Measurements And p38 | Final payment of retention shall be in conformance with Public Contract Code Section 7107. It is mutually agreed between the parties to the contract that no certificate given or payments made under the contract, except t
Alternates |  | Section IX. Quantities p40 | The project also includes ZERO add alternates. TABULATION OF PRELIMINARY ESTIMATE OF QUANTITIES
Addenda acknowledgement |  | Section IV. Control p29 | Contractor shall acknowledge receipt of all addenda on the Bid and those Bids that do not have acknowledgment of all addenda will be considered non-responsive. In the event of any discrepancy between any drawing and the
Required bid forms / exhibits | 14 exhibits (A–N), 7 attachments | p2 | Exhibit A: Bidder's Proposal; Exhibit B: Contractor's Certified Payroll Forms; Exhibit C: List of Processors; Exhibit D: Contractor Agreement; Exhibit E: Emergency Form; Exhibit F: Performance Bond Form; Exhibit G: Payme
Not found in this document: |  |  | Substitution request deadline
HIDDEN COSTS (12) - scope you pay for without a pay item | What to carry | Where | Clause
Contractor bears cost | cost falls on you - price it | p14 | The Contractor shall rebuild, repair, restore and make good all injuries or damages to any portion of the work occasioned by any of the above causes before final acceptance and shall bear the expense thereof, except such
Included in unit / lump-sum price | price it into the named unit/lump-sum item | p28 | Full compensation for furnishing all working drawings and digital as-built drawings shall be considered as included in the prices paid for the various contract items of work, and no additional allowance will be made ther
At Contractor's expense | cost falls on you - price it | p29 | G. CONSTRUCTION STAKING & LAYOUT. Construction staking and layout shall be at the contractor's expense and performed by the contractor's surveyor or engineer qualified to do surveying work.
At Contractor's expense | cost falls on you - price it | p35 | …same for the purpose of completing said contract, and hire such force and buy or rent such additional machinery, tools, appliances, and equipment, and buy such additional materials and supplies at the Contractor's expen
No additional compensation | cost falls on you - price it | p46 | No additional compensation will be allowed the Contractor for providing for the free passage of traffic through the work.
At Contractor's expense | cost falls on you - price it | p49 | Any permanent survey points and/or monuments disturbed or destroyed, as a direct or indirect result of construction activity shall be replaced to the satisfaction of the Engineer by a licensed surveyor at the Contractor'
No additional compensation | cost falls on you - price it | p49 | Unless specified separately by bid items, payment for existing improvements should be included in various bid items and no additional payment will be made.
Included in unit / lump-sum price | price it into the named unit/lump-sum item | p50 | Full compensation for this work shall be considered as included in the prices paid for the various contract items of work, and no additional allowance will be made.
No cost to Owner | cost falls on you - price it | p51 | Planned utility service shutdowns shall be accomplished during periods of minimum use. In some cases this may require night or weekend work, at no additional cost to the City.
Contractor bears cost | cost falls on you - price it | p51 | The cost of repair shall be borne by the Contractor.
At Contractor's expense | cost falls on you - price it | p52 | Any damage or collapse of pavement or improvements beyond the trench shoring or excavation limits, due to sliding, caving, or settling of ground during excavation, construction, or backfilling, or from construction equip
No separate payment | carry this cost inside another bid item | p56 | Full compensation for temporary delineation shall be considered as included in the prices paid for the contract items of work that obliterated the existing delineation and no separate payment will be made therefore.
NAMED PRODUCTS | Count
GLOBAL OR-EQUAL CLAUSE - every trade name substitutable unless stated otherwise | 1
SUBMITTALS (28) | Count
Plans / procedures | 10
From the spec's submittal schedule | 9
Permits / insurance / payroll | 6
Certificates | 4
Calculations / design | 2
Samples | 1
Schedule | 1
Product data | 1
Qualifications | 1
COSTLY ITEMS (10) | Why it costs | Pages
[universal] Traffic control | traffic plan, flaggers, devices | p15, p25, p30, p33, p43, p46, p47, p57,
[universal] Special inspections | inspection coordination and fees | p30, p148, p149, p150, p151, p152, p153,
[universal] Stormwater / erosion control | compliance and BMPs | p16, p17, p18, p19, p21, p23, p94, p401
[universal] Dewatering | pumps, permits, discharge | p13, p17, p51, p52, p53, p55
[universal] Restricted working hours | overtime / night-shift premium | p15, p46, p47, p51
[universal] Hazardous materials | abatement subcontractor | p87, p143, p401
[universal] Permits and fees | permit costs | p13, p94
[concrete] Sandblast / bush-hammer / exposed aggregate | extra surface-finishing labor | p49
[mep] Commissioning | commissioning support labor | p122
[universal] Record / as-built drawings | documentation cost | p28
TOP RFIs TO SEND (18 total) | Risk | Where | Draft RFI
Scope set later by the Engineer | High | p14 | Ref. Section II. Legal Relations And Responsibilities, p.14: "The Contractor shall furnish, erect and maintain such fences, barriers, lights and signs as are necessary or as required by the Engineer to give adequate warning to the public at all times that the work is in progress…" - Please define th
Scope set later by the Engineer | High | p27 | Ref. Section III. Scope Of Work, p.27: "D. REMOVAL OF OBSTRUCTIONS. The Contractor shall remove and dispose of all structures, debris, or other obstruction of any character to the construction of the project if and as required by the Engineer." - Please define the extent / quantity so it can be pric
Scope set later by the Engineer | High | p48 | Ref. Section XII. Construction Details, p.48: "E. DISPOSAL OF EXCAVATED MATERIALS. Salvable materials will be disposed of as directed by the Engineer." - Please define the extent / quantity so it can be priced. As written, scope is decided later.
Risk assumed by bidder | High | p51 | Ref. Section XII. Construction Details, p.51: "It should be presumed that the presence of high groundwater will require dewatering operations." - Please confirm the assumption to price, or provide the data (e.g. geotech) so it can be priced rather than guessed.
Scope set later by the Engineer | High | p56 | Ref. Section XII. Construction Details, p.56: "Striping for all other locations within the project boundaries shall be replaced in kind across full width of roadway, as directed by the Engineer." - Please define the extent / quantity so it can be priced. As written, scope is decided later.
Scope set later by the Engineer | High | p187 | Ref. Exhibit N, p.187: "…foundation for the pipe in the opinion of the Director of the Public Works, the unsuitable material shall be removed as directed by the Director of Public Works to provide a stable and satisfactory…" - Please define the extent / quantity so it can be priced. As written, scop
Undefined acceptance criteria | Medium | p16 | Ref. Section II. Legal Relations And Responsibilities, p.16: "…damaged or interrupted, the Contractor shall immediately, at his/her own expense, restore such services in a manner satisfactory to the City…" - Please give measurable acceptance criteria (tolerance, test, standard).
Undefined acceptance criteria | Medium | p47 | Ref. Section XII. Construction Details, p.47: "The City will not compensate the Contractor for any work associated with replacing striping/marking to the satisfaction of the Engineer, including but not limited to: the full removal of the rejected traffic striping…" - Please give measurable acceptanc

## Bid-Killers
Bid-killer | Key value | Clause | Section | Page | Also on pages | Confidence | Notes
Bid due date / opening | Wednesday, September 8, 2021; 2:01 p.m | Bids will be opened in the Public Works Department, 950 W. Mall Square, Room 110, Alameda, California, at 2:01 p.m. on Wednesday, September 8, 2021. F. BIDDER'S GUARANTY. All bids shall be accompanied by one of the following forms of bidder's guaranty: cash, a cashier's check, a certified check, or a bidder's bond executed by an admitted surety insurer, made payable to the… | Section I. Proposal And Contract Requirements | 6 | p1 | HIGH | verify the value against the page
Mandatory pre-bid / job-walk | Wednesday, August 18, 2021 at 11:00 am | A mandatory pre-bid meeting will be held at City Hall West, 950 W. Mall Square, Conference Room 156, Alameda, California, 94501 on Wednesday, August 18, 2021 at 11:00 am. City reserves the right to hold additional prebid meetings as necessary for contractors to visit the site. | Section I. Proposal And Contract Requirements | 6 | p1, p29 | HIGH | verify the value against the page
RFI / questions deadline | submit an RFI within five (5) business days | X. SUBMITTALS AND REQUEST FOR INFORMATION (RFI'S). The Contractor shall submit an RFI within five (5) business days of an event or question of fact arising under the Contract. The Engineer in cha | Section II. Legal Relations And Responsibilities | 21 |  | HIGH | this is the construction-phase RFI process, not a pre-bid questions cutoff - check the bid invitation for one
Substitution request deadline |  | NOT FOUND |  |  |  | - | not detected - confirm it truly does not apply before relying on it
Bid bond / bid security | 10% | The security shall be in an amount equal to at least ten percent (10%) of the amount bid. A bid shall not be considered unless one of the forms of bidder's security is enclosed with it. | Section I. Proposal And Contract Requirements | 6 | p8, p61, p109, p110 | HIGH | verify the value against the page
Performance bond | $25,000 | Faithful Performance Bond and Labor and Material Bond are only required for work over $25,000. Therefore, those estimates that are under $25,000 will not need to budget for the bond premiums and those estimates over $25,000 will need to be sure to budget for the bond premiums. | Exhibit C | 88 | p8, p103, p104, p105 | HIGH | verify the value against the page
Payment bond | $25,000 | Faithful Performance Bond and Labor and Material Bond are only required for work over $25,000. Therefore, those estimates that are under $25,000 will not need to budget for the bond premiums and those estimates over $25,000 will need to be sure to budget for the bond premiums. | Exhibit C | 88 | p106, p107, p108 | HIGH | verify the value against the page
Post-award bonds/insurance deadline |  | No proposal shall be considered binding upon the City until the execution of the contract. Failure to execute a contract and file acceptable bonds and insurance as provided herein within the time frame outlined above shall be just cause for the annulment of the award and the forfeiture of the bidder's guaranty. N. CONTRACT BONDS. The Contractor shall furnish two good and… | Section I. Proposal And Contract Requirements | 8 | p6, p96, p113 | HIGH | verify the value against the page
Bid validity period | 90 days | In the event of a delay the City reserves the right to hold the Bidder to its bid for 90 days from the date the contract is awarded. Bid protests, contracts, bonds, insurance, and other documents identified in these specifications and these special provisions are to be delivered to the following City address: City of Alameda, City Hall West, Public Works Department, 950 West… | Section I. Proposal And Contract Requirements | 7 |  | HIGH | verify the value against the page
Liquidated damages | $2,500.00 per day | E. TIME OF COMPLETION AND LIQUIDATED DAMAGES. It is agreed by the parties to the contract that in case all the work called for under the contract is not completed before or upon the expiration of the contract's term as set forth in these specifications, damage will be sustained by the City of Alameda, and that it is and will be impracticable to determine the actual damage… | Section VI. Prosecution And Progress | 34 | p6, p37, p61, p84, p85 | HIGH | per-day DELAY damages - carry in schedule risk
Per-day penalties / fines | $250.00 per occurrence per day | The fine for noncompliance of the above program is two hundred and fifty dollars ($250.00) per occurrence per day. The State under the Federal Clean Water Act can also impose a fine on the Contractor. | Section II. Legal Relations And Responsibilities | 19 | p34, p84, p94 | HIGH | verify the value against the page
Contract time / completion | two hundred fifty (250) consecutive working days | The Contractor shall have two hundred fifty (250) consecutive working days from the date the work is to commence pursuant to the Notice to Proceed to complete the work. Contractor is advised to remove all equipment from the streets identified as route, detour, and/or staging areas for the 4th of July Parade 2022. | Section III. Scope Of Work | 25 |  | HIGH | verify the value against the page
Insurance requirement |  | …terms of this Agreement, Contractor shall furnish the City's Risk Manager with certificates showing the type, amount, class of operations covered, effective dates and dates of expiration of insurance coverage in compliance with paragraphs 10A, B, C and D. Such certificates, which do not limit Contractor's indemnification, shall also contain substantially the following… | Exhibit C | 86 | p8, p87, p88, p89 | HIGH | verify the value against the page
Prevailing wage / Davis-Bacon | $50.00 for each calendar day | …Industrial Relations determines that there has been a change in any prevailing rate of per diem wages in the locality in which this public work is to be performed, such change shall not alter the wage rates in the Notice calling for Bids or the contract subsequently awarded. Pursuant to Labor Code •1775, the Contractor shall as a penalty to the City, forfeit Fifty Dollars… | Section II. Legal Relations And Responsibilities | 10 | p9, p11, p12, p64, p67, p68, p70, p92, p122, p123, p137, p141 | HIGH | verify the value against the page
Required contractor license | "A" license or a "C" license | All Contractors must have an "A" license or a "C" license that allows them to complete the work specified herein, in a professional manner consistent with these specifications. J. PERMITS AND LICENSES. The Contractor shall procure all permits and licenses, including City of Alameda business licenses, pay all charges and fees, and give all notices necessary and incidental to… | Section II. Legal Relations And Responsibilities | 13 | p12, p93 | HIGH | verify the value against the page
Retainage |  | Final payment of retention shall be in conformance with Public Contract Code Section 7107. It is mutually agreed between the parties to the contract that no certificate given or payments made under the contract, except the final certificate of final payment, shall be conclusive evidence of the performance of the contract, either wholly or in part, against any claim of the… | Section VII. Measurements And Payment | 38 | p84 | HIGH | verify the value against the page
Alternates |  | The project also includes ZERO add alternates. TABULATION OF PRELIMINARY ESTIMATE OF QUANTITIES | Section IX. Quantities | 40 |  | HIGH | verify the value against the page
Addenda acknowledgement |  | Contractor shall acknowledge receipt of all addenda on the Bid and those Bids that do not have acknowledgment of all addenda will be considered non-responsive. In the event of any discrepancy between any drawing and the figures written thereon, the figures shall be taken as correct. | Section IV. Control | 29 | p5 | HIGH | verify the value against the page
Required bid forms / exhibits | 14 exhibits (A–N), 7 attachments | Exhibit A: Bidder's Proposal; Exhibit B: Contractor's Certified Payroll Forms; Exhibit C: List of Processors; Exhibit D: Contractor Agreement; Exhibit E: Emergency Form; Exhibit F: Performance Bond Form; Exhibit G: Payment Bond Form; Exhibit H: Bidder's Bond; Exhibit I: List of Submittals; Exhibit J: City's Integrated Pest Management Plan; Exhibit K: Project Stabilization Agreement; Exhibit L: Standardization of Major Equipment Components for; Exhibit M: Special Inspection and Testing Agreement Form; Exhibit N: Pedestrian and Traffic Control Plan Application Form and Checklist ¦ Attachments: A: Trench Excavation Construction Standards; B: Geotechnical Evaluation, Golf Course Pump Station Electrical Control; C: Applicable City of Alameda Standard Plans and Details; D: BCDC Regionwide Permit No. RWP-2 for the work at the Webster Street; E: Geotechnical Evaluation, CAT/RAMP 3rd Street Pump Station, Ninyo &; F: Subsurface Investigation Report, 3rd Street Pump Station, Ninyo & Moore,; G: City of Alameda Marsh Crust Permit Application |  | 2 |  | HIGH | complete every form - an incomplete bid form can get the proposal rejected

## Hidden Costs
Hidden cost | Clause | What to carry | Section | Page | Also on pages | Confidence
Contractor bears cost | The Contractor shall rebuild, repair, restore and make good all injuries or damages to any portion of the work occasioned by any of the above causes before final acceptance and shall bear the expense thereof, except such injuries or damages occasioned by acts of the Federal Government or the public enemy. | cost falls on you - price it | Section II. Legal Relations And Responsibilities | 14 |  | HIGH
Included in unit / lump-sum price | Full compensation for furnishing all working drawings and digital as-built drawings shall be considered as included in the prices paid for the various contract items of work, and no additional allowance will be made therefor. | price it into the named unit/lump-sum item | Section IV. Control | 28 |  | HIGH
At Contractor's expense | G. CONSTRUCTION STAKING & LAYOUT. Construction staking and layout shall be at the contractor's expense and performed by the contractor's surveyor or engineer qualified to do surveying work. | cost falls on you - price it | Section IV. Control | 29 |  | HIGH
At Contractor's expense | …same for the purpose of completing said contract, and hire such force and buy or rent such additional machinery, tools, appliances, and equipment, and buy such additional materials and supplies at the Contractor's expense as may be necessary for the proper conduct of the work and for the completion thereof; or may employ other parties to substitute other machinery or… | cost falls on you - price it | Section VI. Prosecution And Progress | 35 |  | HIGH
No additional compensation | No additional compensation will be allowed the Contractor for providing for the free passage of traffic through the work. | cost falls on you - price it | Section XII. Construction Details | 46 |  | HIGH
At Contractor's expense | Any permanent survey points and/or monuments disturbed or destroyed, as a direct or indirect result of construction activity shall be replaced to the satisfaction of the Engineer by a licensed surveyor at the Contractor's expense. | cost falls on you - price it | Section XII. Construction Details | 49 |  | HIGH
No additional compensation | Unless specified separately by bid items, payment for existing improvements should be included in various bid items and no additional payment will be made. | cost falls on you - price it | Section XII. Construction Details | 49 |  | HIGH
Included in unit / lump-sum price | Full compensation for this work shall be considered as included in the prices paid for the various contract items of work, and no additional allowance will be made. | price it into the named unit/lump-sum item | Section XII. Construction Details | 50 |  | HIGH
No cost to Owner | Planned utility service shutdowns shall be accomplished during periods of minimum use. In some cases this may require night or weekend work, at no additional cost to the City. | cost falls on you - price it | Section XII. Construction Details | 51 |  | HIGH
Contractor bears cost | The cost of repair shall be borne by the Contractor. | cost falls on you - price it | Section XII. Construction Details | 51 |  | HIGH
At Contractor's expense | Any damage or collapse of pavement or improvements beyond the trench shoring or excavation limits, due to sliding, caving, or settling of ground during excavation, construction, or backfilling, or from construction equipment, shall be repaired to the satisfaction of the Engineer at the Contractor's expense. | cost falls on you - price it | Section XII. Construction Details | 52 |  | HIGH
No separate payment | Full compensation for temporary delineation shall be considered as included in the prices paid for the contract items of work that obliterated the existing delineation and no separate payment will be made therefore. | carry this cost inside another bid item | Section XII. Construction Details | 56 |  | HIGH

## Sole-Source
Classification | Product | Manufacturer(s) | Clause | Section | Page | Also on pages | Confidence
GLOBAL OR-EQUAL CLAUSE - every trade name substitutable unless stated otherwise | ALL NAMED PRODUCTS |  | or the mention of any patented product in the specifications, they shall be deemed to read "or their equals in quality and utility" where two or more such trade names or patented products are mentioned. | Section XII. Construction Details | 48 |  | HIGH

## Submittals
Type | Submittal | Timing | Reference | Section | Page | Also on pages | Confidence
From the spec's submittal schedule | Contract Bonds |  | Section I, Paragraph N | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Certified Payroll | Within 5 days of award | Section II, Paragraph F | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Emergency Form |  | Exhibit E | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Insurance | Submitted weekly | Contract, Exhibit D | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Licenses/Permits |  | Section II, Paragraph J | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Traffic Control Plan | Preconstruction meeting | Section XII, Paragraph A | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Technical Submittals |  | Relevant Technical Specifications | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Stormwater PPP |  | Section II, Paragraph U | Exhibit I | 113 |  | HIGH
From the spec's submittal schedule | Work Schedule | Preconstruction meeting | Section VI, Paragraph A | Exhibit I | 113 |  | HIGH
Permits / insurance / payroll | Each payroll submitted shall be accompanied by a "Statement of Compliance", signed by the Contractor or subcontractor or his/her agent who pays or supervises the payment of the persons employed under the contract, and shall certify the following: |  |  | Section II. Legal Relations And Responsibilities | 11 |  | HIGH
Permits / insurance / payroll | If the Contractor or a subcontractor does not work during the payroll period, a Statement of Non-Working Days must be submitted for each day not worked. |  |  | Section II. Legal Relations And Responsibilities | 12 |  | HIGH
Plans / procedures, Calculations / design | Contractor shall submit to the Engineer at the pre-construction meeting a Pedestrian and Traffic Control Plan, signed and stamped by a Traffic Engineer registered in the State of California, and a completed Application Form and Checklist, included as Exhibit N, for any work that will impact vehicular traffic in the area. | at the pre-construction meeting |  | Section II. Legal Relations And Responsibilities | 15 |  | HIGH
Plans / procedures | V. RECYCLING OF CONCRETE AND ASPHALT MATERIALS. Concrete and Asphalt are highly recyclable, and must be source separated as much as possible on the project site and delivered to a processor as separate materials to ensure a very high recycling rate, above 80%. Additionally, the Contractor shall prepare and submit to Alameda.WasteTracking.com a Waste Management Plan to recycle… |  |  | Section II. Legal Relations And Responsibilities | 20 |  | HIGH
Samples | Representative preliminary samples of the character and quality prescribed shall be submitted by the Contractor or producer of all materials to be used in the work for testing or examination as desired by the Engineer. |  |  | Section V. Control Of Material | 32 |  | HIGH
Schedule | The Contractor shall submit a three week look-ahead work schedule every Monday and upon the issuance of any change order that alters the contract's schedule. |  |  | Section VI. Prosecution And Progress | 33 |  | HIGH
Plans / procedures | The Contractor shall submit additions to the Pedestrian and Traffic Control Plan(s) ten (10) working days in advance of any work that was not covered by the Pedestrian and Traffic Control Plan(s) submitted in the Initial Project Submittal Package. |  |  | Section VI. Prosecution And Progress | 33 |  | HIGH
Plans / procedures | A Pedestrian and Traffic Control Plan(s) identifying the size and location of such facilities shall be submitted to the Engineer for approval a minimum of two weeks prior to beginning construction. | minimum of two weeks prior to beginning construction |  | Section XII. Construction Details | 46 |  | HIGH
Plans / procedures, Calculations / design | Contractor shall submit to the Engineer a Pedestrian and Traffic Control Plan(s) signed and stamped by a Traffic Engineer registered in the state of California for any work that will impact vehicular, bicycle, and pedestrian traffic in the area and shall be developed to show the actual field conditions and not a typical plan. |  |  | Section XII. Construction Details | 46 |  | HIGH
Plans / procedures | Contractor shall submit Pedestrian and Traffic Control Plan(s) for approval to the Engineer at the pre-construction meeting. | at the pre-construction meeting |  | Section XII. Construction Details | 46 |  | HIGH
Product data, Plans / procedures | Contractor shall submit to the Engineer a submittal for the trenching plan, material data sheets of any shoring equipment to be used, and calculations signed, stamped and approved by a registered California Engineer. |  |  | Section XII. Construction Details | 51 |  | HIGH
Plans / procedures | • Pedestrian and Traffic Control Plan for each site |  |  | Section XIII. Mandatory Pre-Construction Meeting Submittals | 57 |  | MEDIUM
Plans / procedures | • Site-Specific Health and Safety Plan (per Health Officer Order 20-10, Appendix B-2, Large Construction Project Safety Protocol) |  |  | Section XIII. Mandatory Pre-Construction Meeting Submittals | 57 |  | MEDIUM
Certificates | Executed Agreement to be Bound to PSA Security For Compensation Certificate Important Instructions |  |  | Section XIII. Mandatory Pre-Construction Meeting Submittals | 58 |  | MEDIUM
Certificates, Permits / insurance / payroll | Endorsements naming the City, its City Council, boards, commissions, officials, employees, agents and volunteers as additional insured shall be submitted with the insurance certificates. |  |  | Exhibit C | 86 |  | HIGH
Certificates, Permits / insurance / payroll | employment of Local Residents goal on this Project, the Contractor/Employer(s) shall submit copies of their monthly certified payroll reporting forms to the Coordinator. | monthly |  | Exhibit K | 136 |  | HIGH
Qualifications | Inspection agency to submit names and qualifications of on-site special inspectors to this Division for approval. |  |  | Exhibit M | 150 |  | HIGH
Certificates, Permits / insurance / payroll | Before an occupancy permit can be issued: A final report of special inspections documenting required special inspections, tests and correction of any discrepancies noted in the inspections shall be submitted prior to issuance of a Certificate of Use and Occupancy (California Building Code Section 1704.1.2). |  |  | Exhibit M | 150 |  | HIGH
Plans / procedures, Permits / insurance / payroll | B. Each Contractor shall submit to the Inspector a copy of its current Annual Excavation Permit issued by CAL/OSHA along with the Contractor's own Trench Safety Plan prior to the start of construction. | prior to the start of construction |  | Exhibit N | 186 |  | HIGH

## Costly Items
Trade | Costly item | Why it costs | Evidence | Section | Page | All pages | Mentions | Confidence | Notes
concrete | Sandblast / bush-hammer / exposed aggregate | extra surface-finishing labor | All decorative landscaping (shrubs, plants, trees, lawn, etc.) and/or hardscaped ground surfaces (exposed aggregate, bricks and mortar, painted concrete, etc.) that are removed, damaged, or destroyed as a direct or indirect result of any work done for this project shall be replaced by the… | Section XII. Construction Details | 49 | p49 | 1 | MEDIUM
mep | Commissioning | commissioning support labor | 2.4.1 This Agreement shall apply to any start-up, calibration commissioning, performance testing, repair, operational revisions to systems and/or subsystems performed after Completion if it is within the scope of the contract for public work unless it is performed by City employees. | Exhibit K | 122 | p122 | 1 | MEDIUM
universal | Special inspections | inspection coordination and fees | The Contractor shall contact the City's representative by 11:00 a.m. the day prior to any special inspections so the City can schedule the inspections. | Section IV. Control | 30 | p30, p148, p149, p150, p151, p152, p153, p154, p155, p156 | 10 | MEDIUM
universal | Record / as-built drawings | documentation cost | The Contractor shall provide as-built drawings at the completion of the work. | Section IV. Control | 28 | p28 | 1 | MEDIUM
universal | Restricted working hours | overtime / night-shift premium | (Night work, if requested by the Contractor, must be approved by the City Engineer.) | Section XII. Construction Details | 47 | p15, p46, p47, p51 | 4 | MEDIUM
universal | Permits and fees | permit costs | Contractor shall apply for and obtain permits from Building Services on projects deemed to be subject to the Marsh Crust Ordinance. | Exhibit C | 94 | p13, p94 | 2 | MEDIUM
universal | Dewatering | pumps, permits, discharge | …protection(s), any silt fencing and fiber rolls to be used, storm drain inlet protections, stabilized construction entrance(s) and exits, site and excavation dewatering activities, vehicle tire wash area(s), vehicle and equipment servicing area(s), and the materials handling and storage… | Section II. Legal Relations And Responsibilities | 17 | p13, p17, p51, p52, p53, p55 | 6 | MEDIUM
universal | Traffic control | traffic plan, flaggers, devices | Contractor shall submit to the Engineer at the pre-construction meeting a Pedestrian and Traffic Control Plan, signed and stamped by a Traffic Engineer registered in the State of California, and a completed Application Form and Checklist, included as Exhibit N, for any work that will impact… | Section II. Legal Relations And Responsibilities | 15 | p15, p25, p30, p33, p43, p46, p47, p57, p113, p157, p158, p159, p160, p161 | 14 | MEDIUM
universal | Stormwater / erosion control | compliance and BMPs | U. CONSTRUCTION SITE CONTROLS. Within five (5) business days of the date the work is to commence pursuant to the NTP the Contractor shall submit an Erosion/Stormwater Pollution Control Plan (WPCP) to the City Engineer for review. | Section II. Legal Relations And Responsibilities | 16 | p16, p17, p18, p19, p21, p23, p94, p401 | 8 | MEDIUM
universal | Hazardous materials | abatement subcontractor | (4) Pollution Prevention: Legal liability required for hazardous materials excavation in the amount | Exhibit C | 87 | p87, p143, p401 | 3 | MEDIUM

## RFI List
Risk | Rank | Ambiguous clause | Draft RFI | Section | Page | Also on pages | Confidence
Scope set later by the Engineer | High | The Contractor shall furnish, erect and maintain such fences, barriers, lights and signs as are necessary or as required by the Engineer to give adequate warning to the public at all times that the work is in progress and of any dangerous conditions to be encountered as a result of the work or of the presence of the Contractor's equipment or machinery. | Ref. Section II. Legal Relations And Responsibilities, p.14: "The Contractor shall furnish, erect and maintain such fences, barriers, lights and signs as are necessary or as required by the Engineer to give adequate warning to the public at all times that the work is in progress…" - Please define the extent / quantity so it can be priced. As written, scope is decided later. | Section II. Legal Relations And Responsibilities | 14 |  | MEDIUM
Scope set later by the Engineer | High | D. REMOVAL OF OBSTRUCTIONS. The Contractor shall remove and dispose of all structures, debris, or other obstruction of any character to the construction of the project if and as required by the Engineer. | Ref. Section III. Scope Of Work, p.27: "D. REMOVAL OF OBSTRUCTIONS. The Contractor shall remove and dispose of all structures, debris, or other obstruction of any character to the construction of the project if and as required by the Engineer." - Please define the extent / quantity so it can be priced. As written, scope is decided later. | Section III. Scope Of Work | 27 |  | MEDIUM
Scope set later by the Engineer | High | E. DISPOSAL OF EXCAVATED MATERIALS. Salvable materials will be disposed of as directed by the Engineer. | Ref. Section XII. Construction Details, p.48: "E. DISPOSAL OF EXCAVATED MATERIALS. Salvable materials will be disposed of as directed by the Engineer." - Please define the extent / quantity so it can be priced. As written, scope is decided later. | Section XII. Construction Details | 48 |  | MEDIUM
Risk assumed by bidder | High | It should be presumed that the presence of high groundwater will require dewatering operations. | Ref. Section XII. Construction Details, p.51: "It should be presumed that the presence of high groundwater will require dewatering operations." - Please confirm the assumption to price, or provide the data (e.g. geotech) so it can be priced rather than guessed. | Section XII. Construction Details | 51 |  | MEDIUM
Scope set later by the Engineer | High | Striping for all other locations within the project boundaries shall be replaced in kind across full width of roadway, as directed by the Engineer. | Ref. Section XII. Construction Details, p.56: "Striping for all other locations within the project boundaries shall be replaced in kind across full width of roadway, as directed by the Engineer." - Please define the extent / quantity so it can be priced. As written, scope is decided later. | Section XII. Construction Details | 56 |  | MEDIUM
Scope set later by the Engineer | High | Whenever the bottom of the trench is soft or rocky, or, otherwise unsuitable as a foundation for the pipe in the opinion of the Director of the Public Works, the unsuitable material shall be removed as directed by the Director of Public Works to provide a stable and satisfactory foundation. | Ref. Exhibit N, p.187: "…foundation for the pipe in the opinion of the Director of the Public Works, the unsuitable material shall be removed as directed by the Director of Public Works to provide a stable and satisfactory…" - Please define the extent / quantity so it can be priced. As written, scope is decided later. | Exhibit N | 187 |  | MEDIUM
Undefined acceptance criteria | Medium | The work will be so prosecuted that a minimum of damage will result to utility services. In the event that utility services are damaged or interrupted, the Contractor shall immediately, at his/her own expense, restore such services in a manner satisfactory to the City Engineer. | Ref. Section II. Legal Relations And Responsibilities, p.16: "…damaged or interrupted, the Contractor shall immediately, at his/her own expense, restore such services in a manner satisfactory to the City…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section II. Legal Relations And Responsibilities | 16 |  | MEDIUM
Undefined acceptance criteria | Medium | The City will not compensate the Contractor for any work associated with replacing striping/marking to the satisfaction of the Engineer, including but not limited to: the full removal of the rejected traffic striping and pavement marking work; the installation of new striping/marking, including blacking out any of the removed and rejected striping/marking; and the re-posting… | Ref. Section XII. Construction Details, p.47: "The City will not compensate the Contractor for any work associated with replacing striping/marking to the satisfaction of the Engineer, including but not limited to: the full removal of the rejected traffic striping…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 47 |  | MEDIUM
Undefined acceptance criteria | Medium | All exposed surfaces shall be cured by the impervious membrane method to the satisfaction of the Engineer. | Ref. Section XII. Construction Details, p.48: "All exposed surfaces shall be cured by the impervious membrane method to the satisfaction of the Engineer." - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 48 |  | MEDIUM
Undefined acceptance criteria | Medium | F. EXISTING IMPROVEMENTS. Existing fence, lawn, or other improvements within the area of the work shall be carefully removed without damage and replaced in their present location and condition upon completion of the work, in a manner satisfactory to the Engineer and the owner. | Ref. Section XII. Construction Details, p.48: "…removed without damage and replaced in their present location and condition upon completion of the work, in a manner satisfactory to the Engineer and the…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 48 |  | MEDIUM
Undefined acceptance criteria | Medium | All existing irrigation system including electric wire, pipelines, sprinkler heads, damaged as a direct or indirect result of construction activity, shall be replaced by the Contractor at his/her expense at appropriate locations in a manner satisfactory to the Engineer and the owner. | Ref. Section XII. Construction Details, p.49: "…construction activity, shall be replaced by the Contractor at his/her expense at appropriate locations in a manner satisfactory to the Engineer and the…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 49 |  | MEDIUM
Undefined acceptance criteria | Medium | Any existing improvements that are damaged or disturbed due to carelessness by the Contractor shall be replaced or adjusted to the satisfaction of the Engineer. | Ref. Section XII. Construction Details, p.49: "Any existing improvements that are damaged or disturbed due to carelessness by the Contractor shall be replaced or adjusted to the satisfaction of the Engineer." - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 49 |  | MEDIUM
Undefined acceptance criteria | Medium | Existing fence or other improvements within the area of the work shall be carefully removed without damage and replaced in their present location and condition upon completion of the work, in a manner satisfactory to the Engineer and the owner. | Ref. Section XII. Construction Details, p.49: "…removed without damage and replaced in their present location and condition upon completion of the work, in a manner satisfactory to the Engineer and the…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 49 |  | MEDIUM
Undefined acceptance criteria | Medium | Any permanent survey points and/or monuments disturbed or destroyed, as a direct or indirect result of construction activity shall be replaced to the satisfaction of the Engineer by a licensed surveyor at the Contractor's expense. | Ref. Section XII. Construction Details, p.49: "…and/or monuments disturbed or destroyed, as a direct or indirect result of construction activity shall be replaced to the satisfaction of the Engineer by a licensed surveyor at the Contractor's…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 49 |  | MEDIUM
Undefined acceptance criteria | Medium | …concrete, etc.) that are removed, damaged, or destroyed as a direct or indirect result of any work done for this project shall be replaced by the contractor at his expense and in the manner that is satisfactory to the engineer and the… | Ref. Section XII. Construction Details, p.49: "…of any work done for this project shall be replaced by the contractor at his expense and in the manner that is satisfactory to the engineer and the…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 49 |  | MEDIUM
Undefined acceptance criteria | Medium | Any damage or collapse of pavement or improvements beyond the trench shoring or excavation limits, due to sliding, caving, or settling of ground during excavation, construction, or backfilling, or from construction equipment, shall be repaired to the satisfaction of the Engineer at the Contractor's expense. | Ref. Section XII. Construction Details, p.52: "…settling of ground during excavation, construction, or backfilling, or from construction equipment, shall be repaired to the satisfaction of the Engineer at the Contractor's…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 52 |  | MEDIUM
Undefined acceptance criteria | Medium | Any damage to the existing improvements beyond the trench shoring or excavation limits due sliding, caving, or settling of ground or backfill, or from construction equipment shall be repaired to the satisfaction of the property owner and the City Engineer. | Ref. Section XII. Construction Details, p.55: "…limits due sliding, caving, or settling of ground or backfill, or from construction equipment shall be repaired to the satisfaction of the property owner and the City…" - Please give measurable acceptance criteria (tolerance, test, standard). | Section XII. Construction Details | 55 |  | MEDIUM
Match existing | Medium | The Engineer hereby finds that it is necessary to specify standardized equipment for installation in all of the City's sewer pump stations in order to field test or experiment to determine the equipment's suitability for future use and in order to match existing equipment already in use in other sewer pump stations. | Ref. Exhibit L, p.147: "…stations in order to field test or experiment to determine the equipment's suitability for future use and in order to match existing equipment already in use in other sewer pump…" - Please identify the existing product / provide a sample or spec to match. | Exhibit L | 147 |  | MEDIUM

## Method & Notes
Item | Detail
What this is | Auto-generated spec-review form. Every row is a real sentence from the document, cited to Section + Page. Verify before relying on it.
Documents | sdps_special-provisions-full-07.08.21 (406 pages, 210 blank/near-blank)
Text extractor | C:\Program Files\Git\mingw64\bin\pdftotext.EXE (pdftotext version 4.00)
Confidence | HIGH = literal clause match (still verify the number/date). MEDIUM = keyword or judgment call - read the clause.
NOT FOUND | A bid-killer marked NOT FOUND was not detected. Confirm it truly does not apply - it may be in a document you did not include.
Hidden Costs | Clauses that make you carry cost without a pay item: no separate payment, incidental, at Contractor's expense, no cost to Owner, retesting.
Sole-Source | GLOBAL clause overrides individual rows. LIMITED LIST = only listed manufacturers without a substitution request. NAMED (confirm) = a brand with no substitution language either way.
Submittals | Rows from the spec's own submittal schedule come first, then every sentence requiring a submittal. Claims, notices, RFIs and field sampling are excluded.
Costly Items | Trade watchlists in config/watchlists.json. Price drivers only; boilerplate excluded. One row per item with every page it appears on.
RFI List | Only ambiguity that moves price: unforeseen conditions, assumed risk, scope set later, subjective/undefined acceptance, match existing, undefined standards. Draft RFI ready to paste.
Limits | Text-layer PDFs only (scanned specs need OCR). Tables and drawings are not read. Extraction is high-recall, not zero-noise.